## Sheet1
Testing Booking.com | [6 empty] | E = (a + 4m + b) / 6
№ | Testing Activities | Decomposition | 3-point technique |  |  | Result
|  |  | a | m | b
1 | Planning
1.1 |  | Risk identification | 6 | 13 | 9 | 11.1667
1.2 |  | Determining the Testing Approach | 7 | 15 | 12 | 13.1667
2 | Analysis
2.1 |  | Business requirements | 40 | 60 | 50 | 55
2.2 |  | Functional requirements | 35 | 48 | 41 | 44.6667
2.3 |  | Non-functional requirements | 60 | 85 | 73 | 78.8333
2.4 |  | System requirements | 20 | 35 | 28 | 31.3333
3 | Design
3.1 |  | Create functional test case | 120 | 150 | 135 | 142.5
3.2 |  | Create non-functional test case | 100 | 130 | 125 | 124.1667
3.3 |  | Designing the test environment and tools | 8 | 12 | 10 | 11
3.4 |  | Identifying necessary test data to support test case | 150 | 170 | 165 | 165.8333
4 | Test implementation
4.1 |  | Developing and prioritizing test procedures | 40 | 55 | 47 | 51.1667
4.2 |  | Building the test environment | 25 | 30 | 28 | 28.8333
4.3 |  | Creating test suites from the test procedures | 15 | 20 | 18 | 18.8333
5 | Test execution
5.1 |  | Executing tests either manually or by using test execution tools | 60 | 68 | 64 | 66
5.2 |  | Comparing actual results with expected results | 5 | 7 | 6 | 6.5
5.3 |  | Reporting defects based on the failures | 160 | 180 | 175 | 175.8333
6 | Test completion
6.1 |  | Checking whether all defect reports are closed | 10 | 15 | 12 | 13.6667
6.2 |  | Creating a test summary report to stakeholders | 15 | 18 | 16 | 17.1667
|  |  |  | Total hours |  | 1055.6667